## Project Schedule Estimated
Project Schedule Estimated
Hours |  |  |  |  | Estimated Days |  |  | Data Prep Table
Objective | Section | Step | Name | Hours | Start date | Estimated days to complete | End Date | Date | # Days
1 | A | Research SolidWorks Docs | Research SolidWorks Docs ¦1A | 1 | 2023-01-30 | 7 | 2023-02-06 | 44956 | 7
1 | A | Write test code for starting | Write test code for starting ¦1A | 2 | 2023-01-30 | 2 | 2023-02-01 | 44956 | 2
1 | A | Write test code for attaching | Write test code for attaching ¦1A | 2 | 2023-02-01 | 2 | 2023-02-03 | 44958 | 2
1 | A | Write test code window control | Write test code window control ¦1A | 3 | 2023-02-03 | 3 | 2023-02-06 | 44960 | 3
1 | A | Create library from code | Create library from code ¦1A | 4 | 2023-02-06 | 4 | 2023-02-10 | 44963 | 4
1 | B | Research SolidWorks Docs | Research SolidWorks Docs ¦1B | 1 | 2023-02-10 | 6 | 2023-02-16 | 44967 | 6
1 | B | Write test for listening to events | Write test for listening to events ¦1B | 3 | 2023-02-10 | 3 | 2023-02-13 | 44967 | 3
1 | B | Write a logging utility for events | Write a logging utility for events ¦1B | 2 | 2023-02-13 | 3 | 2023-02-16 | 44970 | 3
1 | B | Create library from code | Create library from code ¦1B | 4 | 2023-02-16 | 5 | 2023-02-21 | 44973 | 5
1 | C | Research SolidWorks Docs | Research SolidWorks Docs ¦1C | 2 | 2023-02-21 | 11 | 2023-03-04 | 44978 | 11
1 | C | Code to list part attributes | Code to list part attributes ¦1C | 3 | 2023-02-21 | 3 | 2023-02-24 | 44978 | 3
1 | C | Code to change part attributes | Code to change part attributes ¦1C | 2 | 2023-02-24 | 2 | 2023-02-26 | 44981 | 2
1 | C | Code to list assembly attributes | Code to list assembly attributes ¦1C | 4 | 2023-02-26 | 4 | 2023-03-02 | 44983 | 4
1 | C | Code to change assembly attributes. | Code to change assembly attributes. ¦1C |  | 2023-03-02 | 2 | 2023-03-04 | 44987 | 2
1 | C | Create library from code | Create library from code ¦1C | 4 | 2023-03-04 | 5 | 2023-03-09 | 44989 | 5
[8 empty] | 0 | 0
2 | A | Learn to create .NET GUIs | Learn to create .NET GUIs ¦2A | 2 | 2023-03-09 | 2 | 2023-03-11 | 44994 | 2
2 | A | Create the desktop GUI for viewing projects | Create the desktop GUI for viewing projects ¦2A | 6 | 2023-03-11 | 5 | 2023-03-16 | 44996 | 5
[8 empty] | 0 | 0
2 | B | Create a form for project creation | Create a form for project creation ¦2B | 4 | 2023-03-16 | 3 | 2023-03-19 | 45001 | 3
2 | B | Create a form for picking pre-existing parts | Create a form for picking pre-existing parts ¦2B | 4 | 2023-03-19 | 3 | 2023-03-22 | 45004 | 3
2 | B | Interface both forms with SolidWorks | Interface both forms with SolidWorks ¦2B | 6 | 2023-03-22 | 4 | 2023-03-26 | 45007 | 4
[8 empty] | 0 | 0
2 | C | Create project properties viewer | Create project properties viewer ¦2C | 4 | 2023-04-03 | 3 | 2023-04-06 | 45019 | 3
2 | C | Use library to interface with SolidWorks | Use library to interface with SolidWorks ¦2C | 3 | 2023-04-06 | 4 | 2023-04-10 | 45022 | 4
[8 empty] | 0 | 0
3 | A | Setup sqlite database | Setup sqlite database ¦3A | 2 | 2023-03-16 | 1 | 2023-03-17 | 45001 | 1
3 | A | Write interface to Flask server | Write interface to Flask server ¦3A | 4 | 2023-03-17 | 2 | 2023-03-19 | 45002 | 2
[8 empty] | 0 | 0
3 | B | Build Flask API | Build Flask API ¦3B | 4 | 2023-03-11 | 3 | 2023-03-14 | 44996 | 3
3 | B | Add local file io | Add local file io ¦3B | 2 | 2023-03-14 | 2 | 2023-03-16 | 44999 | 2
3 | B | Add post requests | Add post requests ¦3B | 2 | 2023-03-16 | 2 | 2023-03-18 | 45001 | 2
|  |  | Total Hours | 80 |  |  |  | 0 | 0
0
|  |  | Select View Option | Estimated
https://www.xelplus.com/quick-gantt-chart/
Formulas:
End Date = [Estimated Days]+[Estimated days to complete]+K7
Estimated Days = [End Date, row above]
Estimated Days = [Estimated Days, row above]

## Project Schedule Actual
Project Schedule Actual
Hours | [6 empty] | Actual Days |  |  | Data
Objective | Section | Step | Name | Hours |  |  | Start date | Actual Days to Complete | End Date | Date | # Days
1 | A | Research SolidWorks Docs | Research SolidWorks Docs ¦1A | 1 |  |  | 2023-01-30 | 2 | 2023-02-01 | 44956 | 2
1 | A | Write test code for starting | Write test code for starting ¦1A | 2 |  |  | 2023-01-30 | 1 | 2023-01-31 | 44956 | 1
1 | A | Write test code for attaching | Write test code for attaching ¦1A | 2 |  |  | 2023-01-30 | 1 | 2023-01-31 | 44956 | 1
1 | A | Write test code window control | Write test code window control ¦1A | 1.5 |  |  | 2023-01-31 | 1 | 2023-02-01 | 44957 | 1
1 | A | Create library from code | Create library from code ¦1A | 2 |  |  | 2023-02-01 | 5 | 2023-02-06 | 44958 | 5
1 | B | Research SolidWorks Docs | Research SolidWorks Docs ¦1B | 3 |  |  | 2023-02-07 | 8 | 2023-02-15 | 44964 | 8
1 | B | Write code to create taskpane | Write code to create taskpane ¦1B | 6 |  |  | 2023-02-09 | 4 | 2023-02-13 | 44966 | 4
1 | B | Write test for listening to events | Write test for listening to events ¦1B | 3 |  |  | 2023-02-13 | 2 | 2023-02-15 | 44970 | 2
1 | B | Write a logging utility for events | Write a logging utility for events ¦1B | 3 | ` |  | 2023-02-15 | 2 | 2023-02-17 | 44972 | 2
1 | C | Research SolidWorks Docs | Research SolidWorks Docs ¦1C | 3 |  |  | 2023-02-18 | 7 | 2023-02-25 | 44975 | 7
1 | C | Code to list part attributes | Code to list part attributes ¦1C | 6 |  | Revision Legend | 2023-02-18 | 4 | 2023-02-22 | 44975 | 4
1 | C | Code to list assembly attributes | Code to list assembly attributes ¦1C | 1 |  | Added | 2023-02-22 | 3 | 2023-02-25 | 44979 | 3
2 | A | Learn to create .NET GUIs | Learn to create .NET GUIs ¦2A | 5 |  | Removed | 2023-03-05 | 4 | 2023-03-09 | 44990 | 4
2 | A | Create the desktop GUI for viewing projects | Create the desktop GUI for viewing projects ¦2A | 4 |  |  | 2023-03-07 | 4 | 2023-03-11 | 44992 | 4
1 | B | Create library for event code | Create library for event code ¦1B | [5 empty] | 0 | 0 | 0
[10 empty] | 0 | 0
1 | C | Code to change part attributes | Code to change part attributes ¦1C | 0 |  |  |  |  | 0 | 0 | 0
1 | C | Code to change assembly attributes. | Code to change assembly attributes. ¦1C | 0 |  |  |  |  | 0 | 0 | 0
1 | C | Create library from code | Create library from code ¦1C | 0 |  |  |  |  | 0 | 0 | 0
[10 empty] | 0 | 0
2 | B | Create a form for project creation | Create a form for project creation ¦2B | 3 |  |  | 2023-03-23 | 1 | 2023-03-24 | 45008 | 1
2 | B | Create a form for picking pre-existing parts | Create a form for picking pre-existing parts ¦2B | 2 |  |  | 2023-03-24 | 1 | 2023-03-25 | 45009 | 1
2 | B | Interface both forms with SolidWorks | Interface both forms with SolidWorks ¦2B | 4 |  |  | 2023-03-25 | 2 | 2023-03-27 | 45010 | 2
[10 empty] | 0 | 0
2 | C | Create project properties viewer | Create project properties viewer ¦2C | 0 |  |  |  |  | 0 | 0 | 0
2 | C | Use library to interface with SolidWorks | Use library to interface with SolidWorks ¦2C | 0 |  |  |  |  | 0 | 0 | 0
[10 empty] | 0 | 0
3 | A | Setup sqlite database | Setup sqlite database ¦3A | 2 |  |  | 2023-03-18 | 1 | 2023-03-19 | 45003 | 1
3 | A | Write interface to Flask server | Write interface to Flask server ¦3A | 6 |  |  | 2022-03-20 | 2 | 2022-03-22 | 44640 | 2
[10 empty] | 0 | 0
3 | B | Build Flask API | Build Flask API ¦3B | 6 |  |  | 2023-03-13 | 5 | 2023-03-18 | 44998 | 5
3 | B | Add local file io | Add local file io ¦3B | 12 |  |  | 2023-03-15 | 7 | 2023-03-22 | 45000 | 7
3 | B | Add post requests | Add post requests ¦3B | 2 |  |  | 2023-03-14 | 2 | 2023-03-16 | 44999 | 2
[10 empty] | 0 | 0
4 | B | Research SolidWorks Docs for Taskpane | Research SolidWorks Docs for Taskpane ¦4B | 2 |  |  | 2023-03-16 | 4 | 2023-03-20 | 45001 | 4
4 | A | Create taskpane dialog | Create taskpane dialog ¦4A | 6 |  |  | 2023-03-17 | 5 | 2023-03-22 | 45002 | 5
4 | A | Interface taskpane with main program | Interface taskpane with main program ¦4A | 8 |  |  | 2023-03-18 | 6 | 2023-03-24 | 45003 | 6
[10 empty] | 0 | 0
4 | B | Debug and test the download process (server/app) | Debug and test the download process (server/app) ¦4B | 14 |  |  | 2023-04-06 | 4 | 2023-04-10 | 45022 | 4
4 | B | Debug and test the upload process (server/app) | Debug and test the upload process (server/app) ¦4B | 10 |  |  | 2023-04-10 | 3 | 2023-04-13 | 45026 | 3
|  |  | Total Hours | 119.5 | [5 empty] | 0 | 0
0
|  |  | Select View Option | Estimated
https://www.xelplus.com/quick-gantt-chart/
Formulas:
End Date = [Actual Days]+[Actual Days to Complete]+N7